## README — Intern Must Read First
AIVI CAREER & CAMPUS OS — INTERN TESTING ASSIGNMENT & SAFETY PROTOCOL
1. What This File Is
This workbook is your complete, authoritative testing assignment for AIVI Career Intelligence OS (B2C SaaS) and Multi-Tenant Campus OS (B2B).
You are testing the end-to-end product user experience, functional workflows, error states, and security guards.
CRITICAL PROTOCOL: All testing runs directly on the Production environment (https://aivilabs.com, Firebase project 'aivi-career').
2. Golden Safety Rules (Breaking ANY rule results in immediate removal from testing)
① Everything you test is the LIVE product — never reset, never delete, never seed, never pay unless the founder is literally sitting next to you running it.
② NEVER click 'Seed Demo Campus' or 'Reset Demo Campus' without Founder present — seeder reset and data purging are strictly founder-only.
③ Use ONLY the official test accounts provided on the 'Test Accounts & Setup' sheet (demo-sunrise campus accounts and founder-approved throwaway B2C account). Do not create other accounts, and do not touch any real user data you encounter.
④ Production uses LIVE Razorpay keys — test card details (e.g. 4111 1111 1111 1111) are NOT supported in live mode. Payment tests are strictly FOUNDER-ONLY live verification (real ₹399 Starter purchase + Razorpay dashboard refund). Interns must NEVER execute live payment transactions.
⑤ Never share credentials, API keys, production URLs, or tracker documents outside the engineering team.
3. Your Daily Workflow (7 Steps)
Step 1: Open 'Test Suites — Master' sheet and filter the 'Suite' column to your assigned daily suite (e.g. S00, S01).
Step 2: Read the 'Preconditions' column carefully BEFORE executing every test case.
Step 3: Execute 'Test Steps' EXACTLY as written — same clicks, same button labels, same inputs, same navigation order.
Step 4: Compare observed UI behavior with 'Expected Result' — you must observe EVERY expected point, not 'mostly'.
Step 5: Set the 'Status' dropdown (Pass / Fail / Blocked / Skipped) and write detailed observations in 'Actual Result'.
Step 6: If FAIL → FIRST run every check in 'If FAIL — Check These First' column AND look up the error message in 'Error Diagnosis Guide'.
Step 7: If still failing after diagnostic checks → file a new bug on 'Bug Log' sheet using the mandatory 5-line format, record the Bug ID, and set Status = Fail.
4. Status Definitions
• Pass: Every single expected point and verbatim error message observed exactly as documented.
• Fail: Any expected point missing, incorrect behavior observed, or unexpected crash occurred AFTER running diagnostic checks.
• Blocked: Cannot execute test case because precondition, service, or test account is unavailable (must record exact blocker reason).
• Skipped: Explicitly instructed by Founder to skip this specific test case (e.g. deprecated staging banner test S11-T001).
5. Severity Guide (Assign when filing bugs on Bug Log)
• P0 (Critical): Login, payment, account deletion, or data loss broken; blocks all testing or crashes app completely.
• P1 (High): Core feature flow broken (e.g. resume scoring fails, drive shortlist excludes eligible students), but clumsy workaround exists.
• P2 (Medium): Secondary feature misbehaves in an edge case or specific browser (e.g. filter dropdown glitch, modal styling issue).
• P3 (Low): Cosmetic issue, text typo, minor alignment defect, or low-priority visual bug.
6. THE 5-LINE BUG FORMAT (Mandatory — Founder accepts ONLY this format)
Line 1: ① What I did: (last 2–3 exact steps taken before failure)
Line 2: ② What I expected: (verbatim expected text/behavior from test case)
Line 3: ③ What happened: (exact verbatim message text — copy it directly, never paraphrase)
Line 4: ④ Where: full URL + environment + exact test account email used
Line 5: ⑤ Evidence: screenshot/screen-recording link in shared Google Drive folder
CRITICAL: No vague 'it didn't work' reports. Any bug report lacking all 5 lines will be rejected and returned to you.
7. The Rule That Ends False Bugs
Before filing ANY bug, you MUST have completed that test's 'If FAIL — Check These First' column AND checked the matching row in 'Error Diagnosis Guide'.
You MUST write 'checks done: [list of checks]' inside the Bug Log row.
Real-Life Example: Login displays 'Invalid email or password' → Checks done: 1) Is email verified in Firebase Console? 2) confirm the URL bar shows https://aivilabs.com (production)? 3) Is password correct (caps lock off)? 4) Try password reset — if reset email arrives, account exists and password was entered wrong! (Marked Not a Bug).

## Test Accounts & Setup
AIVI CAREER & CAMPUS OS — SEEDED ACCOUNTS & ENVIRONMENT SETUP
1. Seeded Test Accounts Inventory (From Chapter 11)
System Role | Display Name | Email Address | Default Password | Custom Claims / Scope | Recommended Test Usage
Platform Admin | Platform Administrator | abhi.triloki@gmail.com | (User Configured) | { role: 'platform_admin' } | Suite S04 Platform Admin Console, tenant provisioning, demo seeder execution
Tenant Admin (TPO) | Dr. Alok Verma | tpo.director@demo.aivilabs.com | DemoUser@2026 | { tenantId: 'demo-sunrise', role: 'tenant_admin' } | Suite S05 TPO Dashboard, placement drives, CSV student import, staff management, billing
Department Coordinator | Prof. Sunita Rao | coordinator.cse@demo.aivilabs.com | DemoUser@2026 | { tenantId: 'demo-sunrise', role: 'coordinator', branchScope: ['CSE'] } | Suite S06 Coordinator branch scoping & CSE student roster management
Student 1 (CSE Batch 26) | Aarav Sharma | student1@demo.aivilabs.com | DemoStudent@2026 | { tenantId: 'demo-sunrise', role: 'student' } | Suite S07 Student drives, resume vault upload, vernacular mock interview (text & voice)
Student 2 (ECE Batch 26) | Aditi Verma | student97@demo.aivilabs.com | DemoStudent@2026 | { tenantId: 'demo-sunrise', role: 'student' } | Suite S07 ECE branch cross-department drive applications
Student 3 (ME Batch 26) | Ananya Gupta | student169@demo.aivilabs.com | DemoStudent@2026 | { tenantId: 'demo-sunrise', role: 'student' } | Suite S07 Mechanical engineering branch student testing
2. Production Environment Details & Gateway Protocol
Environment Property | Production Environment Configuration | QA Safety & Testing Guidelines
Firebase Project ID | aivi-career | Primary production Firebase infrastructure project.
Canonical Web URL | https://aivilabs.com (or https://aivi-career.web.app) | All testing MUST confirm the URL bar shows https://aivilabs.com (production).
Razorpay Key Mode | LIVE Keys (rzp_live_...) | LIVE Mode — Test cards (e.g. 4111 1111 1111 1111) are NOT supported on production.
Payment Test Rule | FOUNDER-ONLY Live Verification | Payment tests are strictly FOUNDER-ONLY using real ₹399 transaction + Razorpay dashboard refund. Interns must NEVER execute transactions.
Permitted Test Accounts | demo-sunrise Campus & Throwaway B2C | You test ONLY with demo-sunrise campus accounts and founder-approved throwaway B2C account. Do not touch real user data.
Destructive Actions | STRICTLY PROHIBITED FOR INTERNS | Seeder reset ('resetDemoCampus'), tenant purging, and account deletions are strictly FOUNDER-ONLY with Founder present.
3. Intern Pre-Testing Setup Checklist
1. Launch Google Chrome browser (latest version).
2. Enable pop-ups for 'aivilabs.com' in Chrome Settings -> Privacy and Security -> Site Settings -> Pop-ups.
3. Enable microphone permissions for 'aivilabs.com' (required for Vernacular Voice Interviews).
4. Bookmark the Production URL (https://aivilabs.com) and keep the shared Google Drive evidence folder open in a separate tab.
5. Confirm the URL bar shows https://aivilabs.com (production) before executing any test case.
4. Sample Inputs for Testing (CSV Import & Negative Test Data)
CSV Import Template Header: Full Name,Email,Enrollment No,Branch,CGPA,Graduation Year
Row Type | Full Name | Email | Enrollment No | Branch | CGPA | Graduation Year / Notes
Valid Row 1 | Rohan Gupta | rohan.gupta@demo.aivilabs.com | SEC26CSE241 | CSE | 8.2 | 2026
Valid Row 2 | Sneha Patel | sneha.patel@demo.aivilabs.com | SEC26ECE242 | ECE | 7.5 | 2026
Valid Row 3 | Vipul Singh | vipul.singh@demo.aivilabs.com | SEC26ME243 | ME | 6.9 | 2026
Bad Row (Duplicate) | Rahul Mishra | rahul.mishra@demo.aivilabs.com | SEC26CSE099 | CSE | 7.1 | 2026 (Duplicate enrollment SEC26CSE099 — expected row error)

## Test Suites — Master
AIVI CAREER & CAMPUS OS — MASTER TEST SUITES TRACKER
Test ID | Suite | Module / Screen | Route / URL | Actor (account) | Preconditions | Test Steps (numbered, one per line) | Expected Result (verbatim strings where known) | If FAIL — Check These First | Severity | Env | Status | Actual Result (what you saw) | Bug ID | Tested By | Date | Source
S00-T001 | S00 — PRODUCTION SMOKE | Landing / Home | / | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/ 2. Observe page header, hero section, and pricing table | Page loads cleanly. Production header renders. No blank screens. | 1. Check internet connection 2. confirm the URL bar shows https://aivilabs.com (production) | P0 | Production | Not Run |  |  |  |  | ch01/§4, ch09/§3
S00-T002 | S00 — PRODUCTION SMOKE | Auth Landing | /auth | Unauthenticated | Browser open | 1. Click 'Sign In' button on header or navigate to /auth | Auth card renders with options: Email/Password login, Signup tab, and 'Continue with Google' button. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check console for script loading errors | P0 | Production | Not Run |  |  |  |  | ch02/Route-2
S00-T003 | S00 — PRODUCTION SMOKE | Staff Login | /campus/login | TPO Admin | TPO account exists | 1. Navigate to /campus/login 2. Enter tpo.director@demo.aivilabs.com and password DemoUser@2026 3. Click 'Sign In' | Authentication succeeds. User lands on /campus showing 'Sunrise Engineering College TPO Command Center'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Is email verified? 3. Is password exact (DemoUser@2026)? | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01, ch11
S00-T004 | S00 — PRODUCTION SMOKE | Campus Dashboard | /campus | TPO Admin | Logged in as TPO Admin | 1. Observe /campus dashboard metrics and AES score band distribution | Dashboard displays student count (242), active drives, and AES score bands (<40, 40-60, 60-75, 75+). | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check if demo campus is seeded (ch.11) | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01
S00-T005 | S00 — PRODUCTION SMOKE | Student Login | /auth | Student 1 | Student account exists | 1. Navigate to /login 2. Enter student1@demo.aivilabs.com and password DemoStudent@2026 3. Click 'Sign In' | Authentication succeeds. SPA redirects student to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Is email verified? 3. Check user claims | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-02, ch11
S00-T006 | S00 — PRODUCTION SMOKE | Student Dashboard | /dashboard | Student 1 | Logged in as Student 1 | 1. Observe B2C SaaS dashboard home | Dashboard displays recent analysis history cards, usage limits, and quick action cards. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify AuthContext state | P1 | Production | Not Run |  |  |  |  | ch02/Route-20
S00-T007 | S00 — PRODUCTION SMOKE | Resume Intelligence | /dashboard/resume | Student 1 | Logged in as Student 1 | 1. Open /dashboard/resume 2. Paste sample resume text (>=50 chars) 3. Click 'Run AI Resume Scoring' | AI analysis completes. Screen displays overall score (0-100), Score Ring, ATS compatibility score, and bullet suggestions. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check remaining Free plan uses 3. Check AI rate limit (3/min) | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-01
S00-T008 | S00 — PRODUCTION SMOKE | Public Contact | /contact | Unauthenticated | Browser open | 1. Navigate to /contact 2. Observe contact form rendering | Contact page renders with name, email, subject, message fields, and 'Send Message' CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) | P2 | Production | Not Run |  |  |  |  | ch02/Route-10
S00-T009 | S00 — PRODUCTION SMOKE | 404 Error Page | /non-existent-page-xyz | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/non-existent-page-xyz | Screen renders branded 404 view: 'Page Not Found', explaining page does not exist, with button 'Return to Home'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check App.tsx wildcard route | P2 | Production | Not Run |  |  |  |  | ch02/§2.1
S00-T010 | S00 — PRODUCTION SMOKE | Mobile Viewport | / | Unauthenticated | Chrome DevTools open (375px) | 1. Open DevTools (F12) -> Toggle Device Toolbar -> Select iPhone SE (375px width) 2. Load / | Responsive layout renders without horizontal overflow or overlapping text. Mobile hamburger menu works. | 1. confirm the URL bar shows https://aivilabs.com (production) | P2 | Production | Not Run |  |  |  |  | ch01/§5
S01-T001 | S01 — AUTH & ONBOARDING | Email Registration | /auth | Public Visitor | Throwaway email ready | 1. Open /auth -> Click 'Sign Up' tab 2. Enter Name 'Test User', email 'qa.throwaway99@demo.aivilabs.com', password 'Password@123' 3. Click 'Create Account' | Account created. SPA redirects to /verify-email showing message: 'Verification email sent to qa.throwaway99@demo.aivilabs.com.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Did user already exist? | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-01
S01-T002 | S01 — AUTH & ONBOARDING | Duplicate Email Signup | /auth | Public Visitor | Existing user email | 1. Open /auth -> Sign Up tab 2. Enter existing email 'student1@demo.aivilabs.com' and password 'Password@123' 3. Click 'Create Account' | Form displays verbatim alert message: 'An account with this email already exists.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-001 mapping in ch.08 | P1 | Production | Not Run |  |  |  |  | ch08/ERR-001
S01-T003 | S01 — AUTH & ONBOARDING | Weak Password Signup | /auth | Public Visitor | Throwaway email ready | 1. Open /auth -> Sign Up tab 2. Enter email 'qa.weakpass@demo.aivilabs.com' and password '12345' (<6 chars) 3. Click 'Create Account' | Form displays verbatim inline error: 'Password should be at least 6 characters.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-002 mapping in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-002
S01-T004 | S01 — AUTH & ONBOARDING | Verified Email Login | /auth | Student 1 | Verified account | 1. Open /login 2. Enter student1@demo.aivilabs.com and password DemoStudent@2026 3. Click 'Sign In' | Authentication succeeds. AuthContext loads custom claims ({ role: 'student', tenantId: 'demo-sunrise' }). Redirects to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify emailVerified is true in auth record | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-02
S01-T005 | S01 — AUTH & ONBOARDING | Unverified Email Login | /auth | Unverified User | Unverified account created in S01-T001 | 1. Open /login 2. Enter qa.throwaway99@demo.aivilabs.com and password Password@123 3. Click 'Sign In' | User is authenticated BUT ProtectedRoute blocks dashboard access. Redirects to /verify-email with banner: 'Email verification required.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ProtectedRoute logic (ch.05) 3. Check ERR-004 in ch.08 | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-02, ch08/ERR-004
S01-T006 | S01 — AUTH & ONBOARDING | Invalid Password Login | /auth | Student 1 | Student account exists | 1. Open /login 2. Enter student1@demo.aivilabs.com and WRONG password 'WrongPassword123' 3. Click 'Sign In' | Form displays verbatim error: 'Invalid email or password.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check caps lock 3. Check ERR-003 in ch.08 | P1 | Production | Not Run |  |  |  |  | ch08/ERR-003
S01-T007 | S01 — AUTH & ONBOARDING | Google OAuth Login | /auth | Public Visitor | Google account ready | 1. Open /auth 2. Click 'Continue with Google' 3. Complete OAuth popup dialog | Google SSO completes. User profile auto-created with emailVerified: true. Redirects to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Allow pop-ups in browser | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-03
S01-T008 | S01 — AUTH & ONBOARDING | Google Popup Closed | /auth | Public Visitor | Browser popups allowed | 1. Open /auth 2. Click 'Continue with Google' 3. Immediately close the Google OAuth popup window | Client catches cancellation. Displays toast: 'Google sign-in popup was closed.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-005 in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-005
S01-T009 | S01 — AUTH & ONBOARDING | Google Popup Blocked | /auth | Public Visitor | Browser popups BLOCKED | 1. Block popups in Chrome settings 2. Open /auth 3. Click 'Continue with Google' | Client catches popup error. Displays alert: 'Popup blocked by browser. Enable popups to sign in with Google.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-006 in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-006
S01-T010 | S01 — AUTH & ONBOARDING | Forgot Password | /auth | Registered User | User email ready | 1. Open /auth 2. Click 'Forgot Password?' 3. Enter email 'student1@demo.aivilabs.com' and click 'Send Reset Link' | Form displays anti-enumeration toast: 'If an account exists for this email, a reset link has been sent.' Password reset email dispatched. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-007 in ch.08 | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-04, ch08/ERR-007
S01-T011 | S01 — AUTH & ONBOARDING | Password Reset Link | /__/auth/action | Registered User | Reset email received | 1. Open password reset link from email 2. Observe URL domain redirection (302 redirect to Firebase domain per ch.02 §2.2) 3. Input new password and submit | Password updated successfully in Firebase Auth. User can log in with new password. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify .htaccess rewrite rule (ch.01 §3.1) | P1 | Production | Not Run |  |  |  |  | ch02/§2.2
S01-T012 | S01 — AUTH & ONBOARDING | Resend Verification | /verify-email | Unverified User | Logged in as unverified user | 1. On /verify-email, click 'Resend Verification Email' button | Toast displays: 'Verification email sent. Please check your inbox.' Cooldown timer activates. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Firebase Auth sendEmailVerification | P2 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-01
S01-T013 | S01 — AUTH & ONBOARDING | Delete Account Precondition | /dashboard/settings | Throwaway User | FOUNDER-ONLY — Throwaway account created for testing | 1. Log in as founder-approved throwaway user created in S01-T001 2. Open /dashboard/settings 3. Scroll to Danger Zone section | FOUNDER-ONLY / FOUNDER-VERIFY — Danger Zone section renders displaying 'Delete Account' button and warning text. | 1. MUST be run BY FOUNDER ONLY on production 2. confirm the URL bar shows https://aivilabs.com (production) | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-05
S01-T014 | S01 — AUTH & ONBOARDING | Delete Account Execution | /dashboard/settings | Throwaway User | FOUNDER-ONLY — Logged in on throwaway account | 1. In Danger Zone, type 'DELETE MY ACCOUNT' into confirmation input 2. Click 'Permanently Delete Account' button | FOUNDER-ONLY / FOUNDER-VERIFY — Everything tested is LIVE product; account deletion strictly founder-gated. | 1. STRICTLY FOUNDER ONLY 2. confirm the URL bar shows https://aivilabs.com (production) | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-AUTH-05
S01-T015 | S01 — AUTH & ONBOARDING | Session Persistence | /dashboard | Student 1 | Logged in as Student 1 | 1. Log in as Student 1 2. Close browser tab 3. Open new tab and navigate to https://aivilabs.com/dashboard | User session persists automatically via browserLocalPersistence. Dashboard loads without requiring re-login. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check client.ts auth persistence setting (ch.01 §1.1) | P1 | Production | Not Run |  |  |  |  | ch05/§1.1
S01-T016 | S01 — AUTH & ONBOARDING | User Sign Out | /dashboard | Student 1 | Logged in as Student 1 | 1. Click user avatar in top header 2. Select 'Sign Out' from dropdown menu | Auth session terminated. User redirected to /auth or landing page. Navigating back to /dashboard redirects to /auth. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AuthContext signOut function | P1 | Production | Not Run |  |  |  |  | ch05/§1.1
S01-T017 | S01 — AUTH & ONBOARDING | Branded Campus Login | /campus/login/demo-sunrise | Public Visitor | Browser open | 1. Navigate to /campus/login/demo-sunrise | Page loads custom Sunrise Engineering College branding: Primary color #169C8F, headline 'Sunrise Engineering College TPO Command Center'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check getTenantBranding endpoint (ch.06/Domain D) | P1 | Production | Not Run |  |  |  |  | ch02/Route-14, ch04/§1.1
S01-T018 | S01 — AUTH & ONBOARDING | Invalid Tenant Code Login | /campus/login/invalid-code-xyz | Public Visitor | Browser open | 1. Navigate to /campus/login/invalid-code-xyz | Page falls back gracefully to default AIVI Campus login styling without breaking. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check fallback branding logic in TenantBrandingContext | P2 | Production | Not Run |  |  |  |  | ch02/Route-14
S02-T001 | S02 — B2C MODULES | Resume Scoring Happy Path | /dashboard/resume | Student 1 | Free plan user | 1. Open /dashboard/resume 2. Paste sample resume text (>=50 chars) 3. Click 'Run AI Resume Scoring' | Analysis runs. Screen displays overall score (0-100), Score Ring, ATS compatibility breakdown, and weak bullet suggestions. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check remaining Free plan resume count | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-01
S02-T002 | S02 — B2C MODULES | Resume Short Text Error | /dashboard/resume | Student 1 | On resume page | 1. Paste text 'Short resume text' (<50 chars) 2. Click 'Run AI Resume Scoring' | Form displays verbatim error toast: 'Resume text is too short to analyze.' No API call made. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-009 in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-009
S02-T003 | S02 — B2C MODULES | Resume Free Limit Hit | /dashboard/resume | Student 1 (Free) | Executed 2 free resume analyses | 1. Attempt 3rd resume analysis on Free plan | Backend checkUsageInline blocks call. Modal pops up displaying verbatim text: 'Free tier limit reached. Upgrade to Starter or Pro for unlimited resume scoring.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-008 in ch.08 3. Inspect user_plans lifetime_resume_count | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-01, ch08/ERR-008
S02-T004 | S02 — B2C MODULES | Job Fit Analysis Happy Path | /dashboard/job-fit | Student 1 | Free plan user | 1. Open /dashboard/job-fit 2. Select resume and paste target JD text 3. Click 'Analyze Job Fit' | Analysis completes. Screen displays overall Match Percentage, Matched Skills, Missing Skills (Critical/Moderate/Minor), and Action Plan. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check remaining Free job fit count | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-02
S02-T005 | S02 — B2C MODULES | Job Fit Missing JD Error | /dashboard/job-fit | Student 1 | On job fit page | 1. Select resume but leave JD field empty 2. Click 'Analyze Job Fit' | Form displays verbatim error toast: 'Please provide both a resume and a job description.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-011 in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-011
S02-T006 | S02 — B2C MODULES | Skill Roadmap Generator | /dashboard/roadmap | Student 1 | Free plan user | 1. Open /dashboard/roadmap 2. Select target role 'Full Stack Developer' 3. Click 'Generate Roadmap' | Generates 30-day, 60-day, and 90-day learning roadmap with recommended free resources and project ideas. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Free roadmap limit (1 count) | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-02
S02-T007 | S02 — B2C MODULES | Interview Prep Question Bank | /dashboard/interview | Student 1 | Free plan user | 1. Open /dashboard/interview 2. Select category 'Technical' 3. Click 'Generate Question Bank' | Renders 5 technical questions with STAR sample answers, key points, and 'Why Asked' interviewer guidance. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SYSTEM_PROMPTS.interview in functions/src/index.ts | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-02
S02-T008 | S02 — B2C MODULES | Promotion Readiness | /dashboard/promotion | Student 1 | Free plan user | 1. Open /dashboard/promotion 2. Select current role 'Junior Engineer' and target role 'Senior Engineer' 3. Click 'Evaluate Readiness' | Displays Readiness Score, Leadership Indicators (Present/Missing), Gap Dimensions (4-6 objects), and Action Plan. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SYSTEM_PROMPTS.promotion | P2 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-02
S02-T009 | S02 — B2C MODULES | Portfolio Analyzer | /dashboard/portfolio | Student 1 | Free plan user | 1. Open /dashboard/portfolio 2. Input project details (Name, Tech Stack, Description) 3. Click 'Analyze Portfolio' | Displays Technical Depth Score, Attractiveness Score, project strengths, and specific improvement suggestions. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SYSTEM_PROMPTS.portfolio | P2 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-02
S02-T010 | S02 — B2C MODULES | LinkedIn Profile Analyzer | /dashboard/linkedin | Student 1 | Free plan user | 1. Open /dashboard/linkedin 2. Paste raw LinkedIn profile text 3. Click 'Analyze Profile' | Displays LinkedIn SSI Score Prediction, Recruiter Search Visibility rating, Headline Strength, and positioning analysis. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check parseLinkedInText helper function in index.ts | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-03
S02-T011 | S02 — B2C MODULES | LinkedIn Optimizer Free Block | /dashboard/linkedin | Student 1 (Free) | Free plan user | 1. On /dashboard/linkedin, click 'Rewrite & Optimize Profile' tab | Backend checkUsageInline blocks call. Returns verbatim error: 'The linkedin optimize feature is only available on Starter or Pro plans.' Pops up UpgradeModal. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-012 in ch.08 3. Verify UpgradeModal opens | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-03, ch08/ERR-012
S02-T012 | S02 — B2C MODULES | LinkedIn Optimizer Paid Tier | /dashboard/linkedin | Starter/Pro User | Paid plan user | 1. Log in as Starter/Pro user 2. Open /dashboard/linkedin 3. Click 'Optimize Profile' | Generates Executive Headline, 3-4 paragraph About section rewrite, quantified experience bullets, and networking hook. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify planType in user_plans is starter or pro | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-B2C-03
S02-T013 | S02 — B2C MODULES | Resume Builder Editor | /dashboard/builder | Starter/Pro User | Paid plan user | 1. Open /dashboard/builder 2. Fill in contact details, work experience, education 3. Click 'Auto-Fill AI Rewrite' | AI rewrites bullet points into ATS-optimized action verb phrases. User can preview and export clean PDF. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check resumeExport.ts utility | P1 | Production | Not Run |  |  |  |  | ch02/Route-32
S02-T014 | S02 — B2C MODULES | Resume Builder PDF Export | /dashboard/builder | Starter/Pro User | Resume builder filled | 1. In /dashboard/builder, click 'Export PDF' | Triggers client PDF generation via jsPDF. Downloads clean ATS-friendly resume PDF file. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify jsPDF download trigger | P2 | Production | Not Run |  |  |  |  | ch02/Route-32
S02-T015 | S02 — B2C MODULES | Analysis History Rendering | /dashboard | Student 1 | Has past analyses | 1. Open /dashboard 2. View 'Recent Analysis History' section | Displays history cards showing past analysis type, date, overall score, and 'View Breakdown' link. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AnalysisHistoryCards component | P2 | Production | Not Run |  |  |  |  | ch01/§5
S02-T016 | S02 — B2C MODULES | Plan Usage Banner | /dashboard | Free User | Free plan user | 1. Log in as Free user 2. Observe top warning banner on dashboard | Banner displays: 'Free Plan: 2 Resume & Job Fit analyses remaining. Upgrade for unlimited access.' with 'Upgrade' button. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check PlanUsageBanner component | P2 | Production | Not Run |  |  |  |  | ch01/§5
S02-T017 | S02 — B2C MODULES | AI Rate Limit Trigger | /dashboard/resume | Student 1 | On resume page | 1. Click 'Run AI Resume Scoring' 4 times rapidly within 30 seconds | 4th call is blocked by rate limiter. Displays verbatim error toast: 'Rate limit exceeded. Try again in a minute.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-013 in ch.08 3. Inspect ai_rate_limits collection | P1 | Production | Not Run |  |  |  |  | ch08/ERR-013
S02-T018 | S02 — B2C MODULES | AI Service Error Fallback | /dashboard/resume | Student 1 | Simulated backend error | 1. Trigger AI call during service outage or simulated invalid API key | Backend catches exception. Displays verbatim error toast: 'AI service is temporarily unavailable. Please try again.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-010 in ch.08 (Organic/backend fallback) | P2 | Production | Not Run |  |  |  |  | ch08/ERR-010
S02-T019 | S02 — B2C MODULES | SEO Freshers Page | /ai-resume-builder-for-freshers | Public Visitor | Browser open | 1. Navigate to /ai-resume-builder-for-freshers | Page renders fresher-specific resume guide, ATS tips, sample templates, and 'Build Fresher Resume' CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SEO pages in App.tsx | P3 | Production | Not Run |  |  |  |  | ch02/Route-15
S02-T020 | S02 — B2C MODULES | SEO Scoring Software Page | /resume-scoring-software | Public Visitor | Browser open | 1. Navigate to /resume-scoring-software | Page renders ATS scoring software comparison table, metric breakdown, and 'Score My Resume' CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SEO pages in App.tsx | P3 | Production | Not Run |  |  |  |  | ch02/Route-16
S02-T021 | S02 — B2C MODULES | SEO Job Fit Tool Page | /job-fit-analysis-tool | Public Visitor | Browser open | 1. Navigate to /job-fit-analysis-tool | Page renders Job Fit analysis tool overview, match methodology, and 'Test Job Match' CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SEO pages in App.tsx | P3 | Production | Not Run |  |  |  |  | ch02/Route-17
S02-T022 | S02 — B2C MODULES | SEO Career Gap Page | /career-gap-analysis-ai | Public Visitor | Browser open | 1. Navigate to /career-gap-analysis-ai | Page renders Career Gap explanation guide, AI mitigation strategies, and 'Analyze Career Gaps' CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SEO pages in App.tsx | P3 | Production | Not Run |  |  |  |  | ch02/Route-18
S02-T023 | S02 — B2C MODULES | SEO LLM Comparison Page | /ai-vs-chatgpt-vs-gemini | Public Visitor | Browser open | 1. Navigate to /ai-vs-chatgpt-vs-gemini | Page renders LLM benchmark comparison (AIVI vs ChatGPT vs Gemini), prompt optimization metrics, and CTA. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SEO pages in App.tsx | P3 | Production | Not Run |  |  |  |  | ch02/Route-19
S03-T001 | S03 — PAYMENTS LIVE-MODE | Upgrade Modal Open | /dashboard | Free User | Logged in as Free user | 1. Click 'Upgrade' button on header or PlanUsageBanner | Upgrade Modal opens displaying plan comparison table: Starter (₹399/mo) and Pro (₹599/mo) with features list. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check UpgradeModal component | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-PAY-01
S03-T002 | S03 — PAYMENTS LIVE-MODE | Create Payment Order | /dashboard | Free User | FOUNDER ONLY — Live Gateway | 1. Select 'Starter Plan (₹399/mo)' 2. Click 'Proceed to Payment' | FOUNDER-ONLY — live payment verification (real ₹399 Starter purchase + Razorpay dashboard refund); interns must not run payment tests | 1. confirm the URL bar shows https://aivilabs.com (production) 2. FOUNDER ONLY live mode | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-PAY-01, ch07/§2
S03-T003 | S03 — PAYMENTS LIVE-MODE | Razorpay Live Payment Execution | /dashboard | Free User | FOUNDER ONLY — Live Gateway | 1. FOUNDER-ONLY verification on LIVE mode. 2. Open Upgrade modal -> Select Starter Plan (₹399/mo) 3. Execute live transaction with real payment method 4. Verify upgrade to Starter plan, then issue immediate refund via Razorpay dashboard. | FOUNDER-ONLY — live payment verification (real ₹399 Starter purchase + Razorpay dashboard refund); interns must not run payment tests | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Verify Razorpay LIVE keys in production env 3. Check user_plans doc in Firestore | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-PAY-01, ch07/§3
S03-T004 | S03 — PAYMENTS LIVE-MODE | Payment Cancellation | /dashboard | Free User | FOUNDER ONLY — Live Gateway | 1. Click 'Proceed to Payment' 2. When Razorpay modal opens, click 'X' (Close) button to dismiss | FOUNDER-ONLY — live payment verification (real ₹399 Starter purchase + Razorpay dashboard refund); interns must not run payment tests | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check paymentService.ts onDismiss handler | P2 | Production | Not Run |  |  |  |  | ch03/FLOW-PAY-01, ch07/§3
S03-T005 | S03 — PAYMENTS LIVE-MODE | Adblocker / Script Blocked | /dashboard | Free User | Adblocker enabled | 1. Enable strict adblocker blocking checkout.razorpay.com 2. Click 'Proceed to Payment' | Script loader times out after 10s. Displays verbatim error toast: 'Unable to load Razorpay checkout script. Please check your network or adblocker/CSP settings.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-014 in ch.08 3. Check loadRazorpay timeout in paymentService.ts | P2 | Production | Not Run |  |  |  |  | ch08/ERR-014
S03-T006 | S03 — PAYMENTS LIVE-MODE | Popup Blocked Modal Error | /dashboard | Free User | Popups blocked | 1. Block popups in browser bar 2. Attempt checkout trigger | Catches popup open exception. Displays verbatim error toast: 'Failed to open Razorpay modal. Please check browser pop-up settings or retry.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-015 in ch.08 | P2 | Production | Not Run |  |  |  |  | ch08/ERR-015
S03-T007 | S03 — PAYMENTS LIVE-MODE | Post-Payment Counter Reset | /dashboard | Starter User | FOUNDER ONLY — Live Gateway | 1. Verify user_plans doc after live payment upgrade | FOUNDER-ONLY — live payment verification (real ₹399 Starter purchase + Razorpay dashboard refund); interns must not run payment tests | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check razorpayWebhook entitlement logic (ch.07 §3) | P1 | Production | Not Run |  |  |  |  | ch07/§3
S03-T008 | S03 — PAYMENTS LIVE-MODE | Upgrade Starter to Pro | /dashboard | Starter User | FOUNDER ONLY — Live Gateway | 1. Click Upgrade -> Select 'Pro Plan (₹599/mo)' 2. Complete live payment | FOUNDER-ONLY — live payment verification (real ₹399 Starter purchase + Razorpay dashboard refund); interns must not run payment tests | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Inspect user_plans planType field | P1 | Production | Not Run |  |  |  |  | ch07/§1
S03-T009 | S03 — PAYMENTS LIVE-MODE | Webhook HMAC Idempotency | /webhooks/razorpay | System Webhook | FOUNDER ONLY ⚠️[FOUNDER-VERIFY] | 1. Simulate duplicate Razorpay webhook event POST to /webhooks/razorpay with same eventId | ⚠️[FOUNDER-VERIFY] Webhook checks payment_events/{eventId}. Ignores duplicate event and returns HTTP 200 without double-crediting. FOUNDER-ONLY. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check razorpayWebhook signature code | P1 | Production | Not Run |  |  |  |  | ch07/§3.2
S03-T010 | S03 — PAYMENTS LIVE-MODE | Settings Plan Details | /dashboard/settings | Starter User | Paid plan user | 1. Open /dashboard/settings 2. View 'Subscription Details' card | Displays active plan ('Starter Plan'), renewal date (paid_until), and 'Manage Subscription' button. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check SettingsPage plan query | P2 | Production | Not Run |  |  |  |  | ch02/Route-30
S03-T011 | S03 — PAYMENTS LIVE-MODE | Invoice Record Verification | /dashboard/settings | Starter User | FOUNDER ONLY ⚠️[FOUNDER-VERIFY] | 1. View payment receipt/invoice entry under billing history | ⚠️[FOUNDER-VERIFY] Displays payment order receipt, date, amount (₹399), and status 'paid' in payment_orders collection. FOUNDER-ONLY. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check payment_orders collection in Firestore | P2 | Production | Not Run |  |  |  |  | ch04/§1.5
S04-T001 | S04 — CAMPUS PLATFORM ADMIN | Platform Admin Console Load | /platform-admin | Platform Admin | Logged in as abhi.triloki@gmail.com | 1. Navigate to /platform-admin | Console loads displaying tenant list, active tenant counts, system stats, and seeder control panel. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check PLATFORM_ADMIN_ALLOWLIST in demoSeeder.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01
S04-T002 | S04 — CAMPUS PLATFORM ADMIN | Non-Admin Access Denied | /platform-admin | Student 1 / TPO Admin | Logged in as non-platform admin | 1. Log in as student1@demo.aivilabs.com 2. Navigate directly to /platform-admin | AdminRoute blocks access. SPA redirects user back to /dashboard (or /campus). | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AdminRoute guard in components/AdminRoute.tsx | P0 | Production | Not Run |  |  |  |  | ch05/§5
S04-T003 | S04 — CAMPUS PLATFORM ADMIN | Seed Demo Campus Execution | /platform-admin | Platform Admin | FOUNDER-ONLY — Run by Founder or with Founder present | 1. On /platform-admin console, click 'Seed Sunrise Demo Campus' button 2. Confirm execution in prompt | FOUNDER-ONLY / FOUNDER-VERIFY — Everything tested is LIVE product; seeder execution strictly founder-gated. | 1. MUST be run BY FOUNDER ONLY on production 2. confirm the URL bar shows https://aivilabs.com (production) 3. Check demo_seed_jobs doc | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01
S04-T004 | S04 — CAMPUS PLATFORM ADMIN | Tenant Provisioning | /platform-admin | Platform Admin | Admin logged in | 1. Click 'Provision New Tenant' 2. Input Name 'Apex Institute', Code 'apex-inst', Plan 'pro', Seats 1000 3. Click 'Provision' | provisionTenant callable function creates tenant doc in /tenants/apex-inst with branding defaults. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check provisionTenant function in index.ts | P1 | Production | Not Run |  |  |  |  | ch06/Domain D
S04-T005 | S04 — CAMPUS PLATFORM ADMIN | Toggle Tenant Status | /platform-admin | Platform Admin | Tenant exists | 1. Locate tenant 'apex-inst' 2. Toggle status switch from Active to Inactive | toggleTenantStatus function updates active: false in Firestore. Members attempting login get tenant suspended message. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check toggleTenantStatus function | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S04-T006 | S04 — CAMPUS PLATFORM ADMIN | Generate Tenant API Key | /platform-admin | Platform Admin | Tenant active | 1. Click 'Generate API Key' for tenant 'demo-sunrise' | generateTenantApiKey function issues an API credential string and stores key record in tenant_api_keys collection. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check tenant_api_keys collection in ch.04 | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S04-T007 | S04 — CAMPUS PLATFORM ADMIN | Reset Demo Campus (Founder Only) | /platform-admin | Platform Admin | FOUNDER-ONLY — Run BY FOUNDER ONLY | 1. Click 'Reset Demo Campus' 2. Enter confirmation phrase 'DELETE DEMO' 3. Submit reset request | ⚠️[FOUNDER-VERIFY] runDemoReset purges all demo-sunrise docs across 8 collections and deletes staff Auth users. STRICTLY FOUNDER ONLY on Production. | 1. STRICTLY FOUNDER ONLY 2. confirm the URL bar shows https://aivilabs.com (production) | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01, ch11/§3.2
S04-T008 | S04 — CAMPUS PLATFORM ADMIN | Public Tenant List API | /campus/login | Public Visitor | Browser open | 1. Open /campus/login dropdown menu | listTenantsPublic function returns list of active tenant names and codes for dropdown selection. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check listTenantsPublic function | P2 | Production | Not Run |  |  |  |  | ch06/Domain D
S05-T001 | S05 — CAMPUS TPO & STAFF | TPO Dashboard Overview | /campus | TPO Admin | Logged in as tpo.director@demo.aivilabs.com | 1. Navigate to /campus | Dashboard loads displaying total student count (242), average AES score (58.4), placement percentage, and AES score bands. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check tenant_daily_stats collection | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01
S05-T002 | S05 — CAMPUS TPO & STAFF | Students Directory Filtering | /campus/students | TPO Admin | On students page | 1. Open /campus/students 2. Select Branch filter 'CSE' and Batch '2026' | Roster updates to display only 96 CSE students. Displays student name, enrollment no, CGPA, AES score, and placement status. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Firestore index (tenantId, branch) | P1 | Production | Not Run |  |  |  |  | ch02/Route-34, ch04/§1.2
S05-T003 | S05 — CAMPUS TPO & STAFF | CSV Student Import Happy Path | /campus/import | TPO Admin | Valid CSV ready | 1. Open /campus/import 2. Drag & drop CSV file with 3 sample rows (Rohan, Sneha, Vipul from ch.11) 3. Map columns and click 'Execute Import' | importStudentsCsv function provisions 3 student Auth accounts, sets custom claims, creates profiles and employability_scores docs. Summary displays: 'Import Complete: 3 Students Created, 0 Errors.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check importStudentsCsv function (ch.03/FLOW-CAMPUS-02) | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-02
S05-T004 | S05 — CAMPUS TPO & STAFF | CSV Duplicate Enrollment Error | /campus/import | TPO Admin | CSV with duplicate ready | 1. Upload CSV containing duplicate enrollment 'SEC26CSE099' (from ch.11 sample) 2. Execute import | Import job completes with row-level error. Summary displays: 'Success: 0, Errors: 1. Row 1: Enrollment SEC26CSE099 already exists.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check import_jobs collection error log | P2 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-02
S05-T005 | S05 — CAMPUS TPO & STAFF | CSV Import History Log | /campus/history | TPO Admin | Import jobs executed | 1. Open /campus/history | Roster renders past CSV import jobs displaying date, processed row count, success count, error count, and status 'completed'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check import_jobs collection in Firestore | P2 | Production | Not Run |  |  |  |  | ch02/Route-36
S05-T006 | S05 — CAMPUS TPO & STAFF | Nudge Student Profile | /campus/students | TPO Admin | On students page | 1. Locate student with incomplete profile 2. Click 'Nudge Student' button | nudgeStudent function dispatches email reminder to student's email address. Displays toast: 'Nudge email sent to student.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check nudgeStudent function in index.ts | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S05-T007 | S05 — CAMPUS TPO & STAFF | Tenant Seat Limit Exceeded | /campus/import | TPO Admin | Tenant seats full ⚠️[FOUNDER-VERIFY] | 1. Attempt CSV import where row count exceeds remaining tenant seats quota | ⚠️[FOUNDER-VERIFY] importStudentsCsv function blocks execution. Displays verbatim error: 'Tenant seat limit reached. Upgrade campus plan to add more students.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-019 in ch.08 3. Compare seatsUsed vs seats in tenant doc | P1 | Production | Not Run |  |  |  |  | ch08/ERR-019
S05-T008 | S05 — CAMPUS TPO & STAFF | Create Placement Drive | /campus/drives | TPO Admin | On drives page | 1. Open /campus/drives -> Click 'Create Drive' 2. Enter Company 'Infosys Specialist', Role 'Systems Engineer' 3. Paste corporate JD text -> Click 'Parse JD with AI' | parseDriveJd uses Gemini AI to extract required skills, min CGPA (6.5), and branch hints. Fills drive form fields automatically. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check parseDriveJd function in index.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S05-T009 | S05 — CAMPUS TPO & STAFF | Publish Placement Drive | /campus/drives | TPO Admin | Drive draft ready | 1. Set minCgpa: 6.5, allowed branches: ['CSE', 'ECE'], CTC: 4.5 LPA 2. Click 'Publish Drive' | publishDrive updates drive status to 'published'. Drive becomes visible to eligible students on their drive dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check placement_drives collection in Firestore | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S05-T010 | S05 — CAMPUS TPO & STAFF | Run AI Shortlist | /campus/drives | TPO Admin | Published drive selected | 1. On drive detail card, click 'Run AI Shortlist' | computeDriveShortlist evaluates student CGPA, AES, and DPDP consent. Populates drive_applications with eligible students. Displays shortlist count (e.g. 38 shortlisted). | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check computeDriveShortlist function in index.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S05-T011 | S05 — CAMPUS TPO & STAFF | Shortlist CGPA Exclusion Check | /campus/drives | TPO Admin | Shortlist computed | 1. Inspect shortlisted students list for drive requiring CGPA >= 6.5 | Students with CGPA < 6.5 (or missing CGPA) are excluded from the shortlist (`eligible: false`). | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check student CGPA in profiles collection | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S05-T012 | S05 — CAMPUS TPO & STAFF | Generate Placement Sprint | /campus/sprints | TPO Admin | Drive published | 1. Open /campus/sprints -> Select drive 'Infosys Specialist' 2. Click 'Generate AI Sprint' | generateDriveSprint calls Gemini to generate a structured 7-day preparation sprint with daily tasks and deep links. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check generateDriveSprint function | P1 | Production | Not Run |  |  |  |  | ch06/Domain E
S05-T013 | S05 — CAMPUS TPO & STAFF | Resume Vault Review & Verify | /campus/vault | TPO Admin | Student resumes submitted | 1. Open /campus/vault -> Select student resume in 'submitted' status 2. Click 'Verify Resume' | verifyResume approves resume. Generates PDF byte buffer stamped with TPO verification QR code (storing verification URL). Updates status to 'verified'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check verifyResume function & pdf-lib stamping (ch.03/FLOW-CAMPUS-01) | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01, ch06/Domain F
S05-T014 | S05 — CAMPUS TPO & STAFF | Request Resume Changes | /campus/vault | TPO Admin | Student resume selected | 1. Select student resume -> Click 'Request Changes' 2. Enter feedback 'Add metrics to project bullet 2' 3. Submit feedback | requestResumeChanges updates vault status to 'changes_requested' and records feedback text. Student receives notification. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check requestResumeChanges function in index.ts | P1 | Production | Not Run |  |  |  |  | ch06/Domain F
S05-T015 | S05 — CAMPUS TPO & STAFF | Accreditation Report Export | /campus/accreditation | TPO Admin | On accreditation page | 1. Open /campus/accreditation 2. Select Report Type 'NAAC Criterion 5 (Student Support & Progression)' 3. Click 'Generate Report' | generateAccreditationReport provisions job in acc_report_jobs. Compiles PDF/CSV report containing student placement stats, AES bands, and drive outcomes. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check acc_report_jobs collection | P1 | Production | Not Run |  |  |  |  | ch06/Domain H
S05-T016 | S05 — CAMPUS TPO & STAFF | Export Audit Logs CSV | /campus/audit-logs | TPO Admin | On audit logs page | 1. Open /campus/audit-logs 2. Click 'Export Audit Logs CSV' | exportAuditLogs compiles system access logs into CSV format and triggers browser download. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check audit_logs collection | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S05-T017 | S05 — CAMPUS TPO & STAFF | Invite Department Coordinator | /campus/staff | TPO Admin | On staff page | 1. Open /campus/staff -> Click 'Invite Staff' 2. Enter Name 'Prof. Rajesh Kumar', Email 'coordinator.ece@demo.aivilabs.com', Branch Scope ['ECE'] 3. Submit invitation | inviteCoordinator provisions coordinator account, sets custom claims { role: 'coordinator', tenantId: 'demo-sunrise', branchScope: ['ECE'] }, and sends invite email. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check inviteCoordinator function in index.ts | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01, ch06/Domain D
S05-T018 | S05 — CAMPUS TPO & STAFF | Deactivate Staff Coordinator | /campus/staff | TPO Admin | Coordinator active | 1. Locate coordinator in staff directory 2. Click 'Deactivate Staff' | deactivateStaff updates custom claims to revoke staff role and deactivates profile doc. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check deactivateStaff function | P2 | Production | Not Run |  |  |  |  | ch06/Domain D
S05-T019 | S05 — CAMPUS TPO & STAFF | Campus Billing Invoices | /campus/billing | TPO Admin | On billing page | 1. Open /campus/billing | Displays current seat usage (242 / 3000), subscription tier ('Pro Plan'), and historical billing invoices list. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check billing_invoices collection | P2 | Production | Not Run |  |  |  |  | ch04/§1.5
S05-T020 | S05 — CAMPUS TPO & STAFF | Update Tenant Branding | /campus/settings | TPO Admin | On tenant settings | 1. Open /campus/settings 2. Change Accent Color to '#FF6D4A' and update login headline 3. Click 'Save Branding Settings' | Updates tenant document branding map. Branded login page at /campus/login/demo-sunrise reflects new color and headline. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check tenants document branding field | P1 | Production | Not Run |  |  |  |  | ch01/§1.1, ch04/§1.1
S05-T021 | S05 — CAMPUS TPO & STAFF | Export Bulk Resume ZIP Package | /campus/vault | TPO Admin | Verified resumes exist | 1. On /campus/vault, select branch 'CSE' -> Click 'Export Resume Package (ZIP)' | exportResumePackage compiles verified student resume PDFs into a single ZIP archive stored in Cloud Storage (/exports/demo-sunrise/...). Returns signed download link. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Storage rules for /exports/ path (ch.10/§2) | P1 | Production | Not Run |  |  |  |  | ch06/Domain F, ch10/§2
S05-T022 | S05 — CAMPUS TPO & STAFF | Generate Parent Report | /campus/students | TPO Admin | Student selected | 1. Select student -> Click 'Generate Parent Progress Report' | generateParentProgressReport generates shareable parent report card PDF/link containing student AES, attendance, and placement status. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check parent_reports collection | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S06-T001 | S06 — COORDINATOR BRANCH SCOPE | Coordinator Login & Scope Check | /campus/login | Coordinator CSE | Logged in as coordinator.cse@demo.aivilabs.com | 1. Log in as coordinator.cse@demo.aivilabs.com 2. Verify custom claims in AuthContext | AuthContext loads custom claims ({ role: 'coordinator', tenantId: 'demo-sunrise', branchScope: ['CSE'] }). | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AuthContext state (ch.05/§2) | P0 | Production | Not Run |  |  |  |  | ch05/§2
S06-T002 | S06 — COORDINATOR BRANCH SCOPE | View Scoped Branch Students | /campus/students | Coordinator CSE | On students page | 1. Open /campus/students | Roster displays ONLY CSE branch students (96 students). Non-CSE students (ECE, ME) are hidden. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check coordinatorBranchAllowed helper in firestore.rules | P0 | Production | Not Run |  |  |  |  | ch05/§2, ch10/§1
S06-T003 | S06 — COORDINATOR BRANCH SCOPE | Out-of-Scope Action Error | /campus/students | Coordinator CSE | Attempting out-of-scope access | 1. Attempt to view or modify an ECE student profile directly via API or URL manipulation | Backend check throws verbatim error: 'Access denied for branch.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-018 in ch.08 3. Check requireTenantAuth branch validation | P1 | Production | Not Run |  |  |  |  | ch08/ERR-018
S06-T004 | S06 — COORDINATOR BRANCH SCOPE | Restricted Staff Management Access | /campus/staff | Coordinator CSE | Logged in as Coordinator | 1. Attempt to open /campus/staff directly in URL bar | TenantRoute guard detects role 'coordinator' (staff management requires 'tenant_admin'). Redirects user back to /campus. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute permissions matrix (ch.05/§5) | P1 | Production | Not Run |  |  |  |  | ch05/§5
S06-T005 | S06 — COORDINATOR BRANCH SCOPE | Restricted Campus Billing Access | /campus/billing | Coordinator CSE | Logged in as Coordinator | 1. Attempt to open /campus/billing directly in URL bar | TenantRoute guard detects role 'coordinator' (billing requires 'tenant_admin'). Redirects user back to /campus. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute permissions matrix (ch.05/§5) | P1 | Production | Not Run |  |  |  |  | ch05/§5
S06-T006 | S06 — COORDINATOR BRANCH SCOPE | Scoped Drive Shortlisting | /campus/drives | Coordinator CSE | On drives page | 1. Open /campus/drives 2. Filter drives for CSE branch | Coordinator can view and run AI shortlists ONLY for drives allowing the 'CSE' branch. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check drive allowedBranches matching branchScope | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S07-T001 | S07 — CAMPUS STUDENT | Student Campus Dashboard | /campus | Student 1 | Logged in as student1@demo.aivilabs.com | 1. Log in as student1@demo.aivilabs.com 2. Navigate to /campus | Student view of campus portal loads displaying personal AES score, active placement drives, assigned sprints, and announcements. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check student profile tenant association | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-04
S07-T002 | S07 — CAMPUS STUDENT | DPDP Consent Modal Check | /campus | Student Opt-Out | Student with dpdpConsent: false | 1. Log in as student with dpdpConsent: false 2. Observe modal prompt | DPDP Privacy Consent Modal pops up explaining data usage rights under India DPDP Act. Requires explicit acceptance before AI features unlock. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check DpdpConsentModal component | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-04
S07-T003 | S07 — CAMPUS STUDENT | DPDP Consent Error Block | /campus/interviews | Student Opt-Out | Consent not accepted | 1. Attempt to launch mock interview without accepting DPDP consent | Backend check throws verbatim error: 'DPDP consent required before running AI analysis.' Features remain locked. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-016 in ch.08 | P1 | Production | Not Run |  |  |  |  | ch08/ERR-016
S07-T004 | S07 — CAMPUS STUDENT | Accept DPDP Consent | /campus | Student Opt-Out | Consent modal open | 1. On DPDP consent modal, click 'I Accept & Grant Consent' | acceptDpdpConsent function updates dpdpConsent: true in profile document. Modal closes and AI features unlock instantly. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check acceptDpdpConsent function in index.ts | P1 | Production | Not Run |  |  |  |  | ch06/Domain D
S07-T005 | S07 — CAMPUS STUDENT | View Campus Placement Drives | /dashboard/drives | Student 1 | Logged in as Student 1 | 1. Open /dashboard/drives | Displays list of active published drives (e.g. TCS Ninja 2026, Wipro Elite 2026) matching student's branch and CGPA eligibility. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check placement_drives collection query | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S07-T006 | S07 — CAMPUS STUDENT | Apply for Placement Drive | /dashboard/drives | Student 1 | Eligible for drive | 1. Select drive 'TCS Ninja 2026' 2. Click 'Apply for Drive' | Creates drive_applications document storing student details, enrollment no, CGPA, and stageIndex: 1. Status shows 'Applied'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check drive_applications collection | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-03
S07-T007 | S07 — CAMPUS STUDENT | Upload Vault Resume | /dashboard/vault | Student 1 | On vault page | 1. Open /dashboard/vault 2. Drag & drop resume PDF 3. Click 'Submit to Campus Vault' | submitVaultResume uploads PDF to Storage (/tenants/demo-sunrise/resumes/...) and creates resume_vault doc with status 'submitted'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check submitVaultResume function in index.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-01, ch06/Domain F
S07-T008 | S07 — CAMPUS STUDENT | Vernacular Mock Interview (Text) | /campus/interviews | Student 1 | Consent accepted | 1. Open /campus/interviews 2. Select Mode 'Text', Language 'English', Target Role 'Software Engineer' 3. Click 'Start Mock Interview' 4. Answer 5 turns and click 'Finish' | Completes full 5-turn interview. finishMockInterview computes overall score, technical rating, fluency rating, and feedback summary. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check startMockInterview and finishMockInterview in index.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-04
S07-T009 | S07 — CAMPUS STUDENT | Vernacular Voice Interview (Hindi) | /campus/interviews | Student 1 | Mic permissions allowed | 1. Select Mode 'Voice', Language 'Hindi' 2. Click 'Start Mock Interview' 3. Allow mic -> Speak answer in Hindi -> Complete turn | answerMockInterviewTurn invokes Bhashini / Voice Engine STT to transcribe spoken Hindi audio into text, evaluates turn, and returns next question audio. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check voiceEngine provider in functions/src/voice/provider.ts | P0 | Production | Not Run |  |  |  |  | ch03/FLOW-CAMPUS-04
S07-T010 | S07 — CAMPUS STUDENT | Microphone Denied Error | /campus/interviews | Student 1 | Mic permissions DENIED | 1. Select Mode 'Voice' 2. Click 'Start Mock Interview' 3. Explicitly click 'Block' on browser microphone prompt | Client catches permission rejection. Displays verbatim error alert: 'Microphone access denied. Please enable mic permissions in browser settings to use voice mode.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ERR-020 in ch.08 | P1 | Production | Not Run |  |  |  |  | ch08/ERR-020
S07-T011 | S07 — CAMPUS STUDENT | Enroll in Prep Sprint | /campus/sprints | Student 1 | Sprint active | 1. Open /campus/sprints -> Select assigned sprint 'TCS Prep Sprint' 2. Click 'Enroll in Sprint' | enrollInSprint creates sprint_enrollments doc. Displays day-by-day task checklist. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check enrollInSprint function | P1 | Production | Not Run |  |  |  |  | ch06/Domain E
S07-T012 | S07 — CAMPUS STUDENT | Mark Sprint Task Complete | /campus/sprints | Student 1 | Enrolled in sprint | 1. On sprint task card, check off Day 1 task 'Run Job Fit Analysis' 2. Click 'Mark Task Done' | markSprintTaskDone updates task completion array in sprint_enrollments doc. Progress bar advances. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check markSprintTaskDone function | P2 | Production | Not Run |  |  |  |  | ch06/Domain E
S07-T013 | S07 — CAMPUS STUDENT | View Campus Announcements | /campus | Student 1 | On campus dashboard | 1. Observe 'Announcements' feed on campus dashboard | Displays active institutional announcements (e.g. 'TCS Drive Drive Briefing at 4 PM'). Student can click 'Mark Read'. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check campus_announcements collection | P2 | Production | Not Run |  |  |  |  | ch04/§1.5
S07-T014 | S07 — CAMPUS STUDENT | Export Drive ICS Calendar | /campus/calendar | Student 1 | On calendar page | 1. Open /campus/calendar -> Select drive event 2. Click 'Export to iCal (.ics)' | getEventIcsFile generates standard .ics calendar file and triggers browser download. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check getEventIcsFile function | P3 | Production | Not Run |  |  |  |  | ch06/Domain H
S07-T015 | S07 — CAMPUS STUDENT | Restricted Staff Directory Access | /campus/students | Student 1 | Logged in as Student | 1. Attempt to open /campus/students directly in URL bar | TenantRoute guard detects role 'student'. Redirects student back to /campus. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute permissions matrix (ch.05/§5) | P1 | Production | Not Run |  |  |  |  | ch05/§5
S07-T016 | S07 — CAMPUS STUDENT | Restricted Import Wizard Access | /campus/import | Student 1 | Logged in as Student | 1. Attempt to open /campus/import directly in URL bar | TenantRoute guard detects role 'student'. Redirects student back to /campus. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute permissions matrix (ch.05/§5) | P1 | Production | Not Run |  |  |  |  | ch05/§5
S08-T001 | S08 — PUBLIC & MARKETING | Landing Page Render | / | Unauthenticated | Browser open | 1. Load https://aivilabs.com/ | Main product landing page loads. Renders hero headline, feature grid, pricing table, and global footer. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Landing.tsx component | P0 | Production | Not Run |  |  |  |  | ch02/Route-1
S08-T002 | S08 — PUBLIC & MARKETING | About Page | /about | Unauthenticated | Browser open | 1. Click 'About Us' link in global footer or navigate to /about | About page loads under PublicPageShell displaying company vision, core metrics, and leadership team. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check About.tsx component | P2 | Production | Not Run |  |  |  |  | ch02/Route-5
S08-T003 | S08 — PUBLIC & MARKETING | How It Works Page | /how-it-works | Unauthenticated | Browser open | 1. Click 'How It Works' in header navigation or navigate to /how-it-works | Page renders detailed 4-step AI analysis pipeline explanation with visual diagrams. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check HowItWorks.tsx component | P2 | Production | Not Run |  |  |  |  | ch02/Route-6
S08-T004 | S08 — PUBLIC & MARKETING | What Is AIVI Page | /what-is-aivi | Unauthenticated | Browser open | 1. Navigate to /what-is-aivi | Page renders conceptual overview of Career Intelligence OS vs traditional ATS keyword matchers. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check WhatIsAivi.tsx component | P3 | Production | Not Run |  |  |  |  | ch02/Route-7
S08-T005 | S08 — PUBLIC & MARKETING | AI Resume Builder Landing | /ai-resume-builder | Unauthenticated | Browser open | 1. Navigate to /ai-resume-builder | Public landing page loads displaying resume template previews and 'Build Resume Now' CTA button. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AIResumeBuilderPage.tsx | P2 | Production | Not Run |  |  |  |  | ch02/Route-8
S08-T006 | S08 — PUBLIC & MARKETING | LinkedIn Optimization Landing | /linkedin-optimization | Unauthenticated | Browser open | 1. Navigate to /linkedin-optimization | Public landing page loads displaying profile SSI optimization steps and 'Optimize Profile' CTA button. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check LinkedInOptimizationPage.tsx | P2 | Production | Not Run |  |  |  |  | ch02/Route-9
S08-T007 | S08 — PUBLIC & MARKETING | Contact Form Submission | /contact | Public Visitor | On contact page | 1. Open /contact 2. Fill Name 'QA Tester', Email 'qa.inquiry@demo.aivilabs.com', Subject 'Demo Inquiry', Message 'Requesting product demo' 3. Click 'Send Message' | submitContactForm callable function fires. Creates contact_messages doc in Firestore and dispatches notification email. Displays success message: 'Thank you! Your message has been sent.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check submitContactForm function in index.ts | P1 | Production | Not Run |  |  |  |  | ch03/FLOW-LEAD-01, ch06/Domain I
S08-T008 | S08 — PUBLIC & MARKETING | Privacy Policy Page | /privacy | Unauthenticated | Browser open | 1. Click 'Privacy Policy' in footer or navigate to /privacy | Privacy policy page loads displaying GDPR & India DPDP Act compliance terms and data retention policies. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Privacy.tsx component | P3 | Production | Not Run |  |  |  |  | ch02/Route-11
S08-T009 | S08 — PUBLIC & MARKETING | Terms of Service Page | /terms | Unauthenticated | Browser open | 1. Click 'Terms of Service' in footer or navigate to /terms | Terms of Service page loads displaying user agreement, payment terms, and subscription policies. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Terms.tsx component | P3 | Production | Not Run |  |  |  |  | ch02/Route-12
S08-T010 | S08 — PUBLIC & MARKETING | Data Processing Addendum Page | /dpa | Unauthenticated | Browser open | 1. Click 'DPA' link or navigate to /dpa | DPA page loads displaying institutional data processing addendum for educational colleges. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check DpaPage.tsx component | P3 | Production | Not Run |  |  |  |  | ch02/Route-49
S08-T011 | S08 — PUBLIC & MARKETING | For Colleges B2B Landing | /for-colleges | Public Visitor | Browser open | 1. Navigate to /for-colleges | B2B institutional landing page loads displaying Campus OS features, TPO metrics, NAAC reporting overview, and 'Request Demo' form. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ForCollegesPage.tsx | P1 | Production | Not Run |  |  |  |  | ch02/Route-50
S08-T012 | S08 — PUBLIC & MARKETING | For Colleges Demo Request | /for-colleges | College Dean / TPO | On for-colleges page | 1. Fill college demo form (College Name, Contact Person, Email, Phone, Student Capacity) 2. Click 'Request Institutional Demo' | Submits institutional lead inquiry. Displays success modal: 'Thank you! Our institutional team will contact you within 24 hours.' | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check contact_messages submission handling | P2 | Production | Not Run |  |  |  |  | ch02/Route-50
S08-T013 | S08 — PUBLIC & MARKETING | Footer Links Verification | / | Unauthenticated | On landing page | 1. Scroll to global footer 2. Click links: About, Features, Pricing, Contact, Privacy, Terms | All footer navigation links route cleanly to their designated page without console errors or broken 404 links. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check GlobalFooter component | P2 | Production | Not Run |  |  |  |  | ch01/§5
S08-T014 | S08 — PUBLIC & MARKETING | Firebase Auth Action Redirect | /__/auth/action | Public Visitor | Simulated email link ⚠️[FOUNDER-VERIFY] | 1. Access URL https://aivilabs.com/__/auth/action?mode=verifyEmail&oobCode=12345 | ⚠️[FOUNDER-VERIFY] Tooling needed to intercept raw HTTP 302 redirect from /__/auth/action to Firebase domain. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check .htaccess rewrite rule (ch.01/§3.1) | P2 | Production | Not Run |  |  |  |  | ch01/§3.1, ch02/§2.2
S09-T001 | S09 — SECURITY GUARDS & PERMISSIONS | Unauthenticated Dashboard Guard | /dashboard | Logged Out User | Clear all session cookies / local storage | 1. Clear browser cookies/storage 2. Attempt to open https://aivilabs.com/dashboard directly | ProtectedRoute guard blocks access. SPA redirects user immediately to /auth. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ProtectedRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T002 | S09 — SECURITY GUARDS & PERMISSIONS | Unverified Dashboard Guard | /dashboard | Unverified User | Logged in on unverified account | 1. Log in as unverified user created in S01-T001 2. Attempt to open /dashboard/resume | ProtectedRoute guard checks emailVerified: false. Redirects user to /verify-email. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check ProtectedRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T003 | S09 — SECURITY GUARDS & PERMISSIONS | B2C User Campus Guard | /campus | B2C User (No Tenant) | Logged in on standard B2C account | 1. Log in as standard B2C user (no tenantId claim) 2. Attempt to navigate to /campus | TenantRoute guard checks tenantId claim: null. Redirects user to /campus/login or /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T004 | S09 — SECURITY GUARDS & PERMISSIONS | Student Staff Guard | /campus/students | Student 1 | Logged in as Student | 1. Log in as Student 1 2. Attempt to open /campus/students directly in URL bar | TenantRoute guard checks role claim: 'student'. Redirects user back to /campus. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check TenantRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T005 | S09 — SECURITY GUARDS & PERMISSIONS | Non-Admin B2C Admin Guard | /dashboard/admin | B2C User / Student | Logged in as non-admin | 1. Log in as B2C user 2. Attempt to open /dashboard/admin directly in URL bar | AdminRoute guard checks isAdmin: false. Redirects user back to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AdminRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T006 | S09 — SECURITY GUARDS & PERMISSIONS | Non-Admin Platform Console Guard | /platform-admin | TPO Admin | Logged in as TPO Admin | 1. Log in as tpo.director@demo.aivilabs.com 2. Attempt to open /platform-admin directly in URL bar | AdminRoute guard checks platform_admin claim: false. Redirects user back to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check AdminRoute component (ch.05/§5) | P0 | Production | Not Run |  |  |  |  | ch05/§5
S09-T007 | S09 — SECURITY GUARDS & PERMISSIONS | Authenticated Auth Route Guard | /auth | Student 1 | Logged in user | 1. Log in as Student 1 2. Attempt to navigate to /auth or /login | Auth component checks user session active. Redirects logged-in user automatically to /dashboard. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Auth.tsx redirect logic | P2 | Production | Not Run |  |  |  |  | ch02/Route-2
S09-T008 | S09 — SECURITY GUARDS & PERMISSIONS | Direct Deep-Link Incognito Check | /dashboard/job-fit | Logged Out User | Fresh Incognito window | 1. Copy URL https://aivilabs.com/dashboard/job-fit 2. Open fresh Incognito window 3. Paste URL and press Enter | SPA loads, evaluates auth state: false, and redirects cleanly to /auth without flashing protected user data. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check Suspense & PageLoader rendering | P1 | Production | Not Run |  |  |  |  | ch02/§2.3
S09-T009 | S09 — SECURITY GUARDS & PERMISSIONS | Direct Storage Bucket URL Access | /tenants/demo-sunrise/resumes/... | Unauthenticated | Browser open | 1. Attempt to open a direct Firebase Storage URL for a student resume without auth token | Cloud Storage security rules block request. Returns HTTP 403 Forbidden. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check storage.rules /tenants/ path rule (ch.10/§2) | P1 | Production | Not Run |  |  |  |  | ch10/§2
S09-T010 | S09 — SECURITY GUARDS & PERMISSIONS | Direct Firestore Client Write Block | /analysis_results | Student 1 | Attempting client SDK write | 1. Open Developer Console on /dashboard 2. Attempt direct db.collection('analysis_results').add({...}) via client SDK | Firestore security rules block write operation (`allow write: if false`). Operation throws permission denied error. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check firestore.rules analysis_results write rule | P0 | Production | Not Run |  |  |  |  | ch10/§1
S09-T011 | S09 — SECURITY GUARDS & PERMISSIONS | Cross-Tenant Data Access Block | /campus/students | Tenant Staff (Tenant B) | Different tenant account ⚠️[FOUNDER-VERIFY] | 1. Log in as staff of Tenant B 2. Attempt to read /profiles where tenantId == 'demo-sunrise' | ⚠️[FOUNDER-VERIFY] Backend security rule test simulating Tenant B staff reading Tenant A profile documents. Enforces hasTenant(tenantId). Access denied. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check hasTenant helper in firestore.rules | P0 | Production | Not Run |  |  |  |  | ch10/§1
S09-T012 | S09 — SECURITY GUARDS & PERMISSIONS | HTTP Security Headers Verification | / | Unauthenticated | DevTools Network Tab open | 1. Open DevTools Network tab -> Inspect main document response headers for https://aivilabs.com/ | Response headers contain: X-Robots-Tag: noindex, nofollow; Strict-Transport-Security; X-Content-Type-Options: nosniff; X-Frame-Options: DENY; Content-Security-Policy. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check firebase.json and .htaccess security headers (ch.01/§3) | P1 | Production | Not Run |  |  |  |  | ch01/§3.1, ch01/§3.2
S10-T001 | S10 — PRODUCTION READ-ONLY SMOKE | Production Home Load | / | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/ 2. Observe page loading and header navigation | Production home page loads cleanly. No staging banner present. Production header renders. | 1. confirm the URL bar shows https://aivilabs.com (production) | P0 | Production | Not Run |  |  |  |  | ch11/§5
S10-T002 | S10 — PRODUCTION READ-ONLY SMOKE | Production For Colleges Load | /for-colleges | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/for-colleges | Institutional B2B landing page loads cleanly. Renders features, metrics, and demo request form. | 1. confirm the URL bar shows https://aivilabs.com (production) | P1 | Production | Not Run |  |  |  |  | ch11/§5
S10-T003 | S10 — PRODUCTION READ-ONLY SMOKE | Production Public Pages | /about | Unauthenticated | Browser open | 1. Load /about, /how-it-works, /privacy, /terms on production domain | All public pages render cleanly without console errors or broken assets. | 1. confirm the URL bar shows https://aivilabs.com (production) | P2 | Production | Not Run |  |  |  |  | ch11/§5
S10-T004 | S10 — PRODUCTION READ-ONLY SMOKE | Production Login Screen | /auth | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/auth | Auth card renders cleanly. DO NOT create fake accounts or run seeder. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. STRICTLY READ-ONLY | P0 | Production | Not Run |  |  |  |  | ch11/§5
S10-T005 | S10 — PRODUCTION READ-ONLY SMOKE | Production Real User Login | /auth | Founder Account Only | Founder credentials | 1. Founder logs in using official real account on production | Authentication succeeds. Dashboard loads user's real data. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. FOR FOUNDER USE ONLY | P0 | Production | Not Run |  |  |  |  | ch11/§5
S10-T006 | S10 — PRODUCTION READ-ONLY SMOKE | Production Dashboard Render | /dashboard | Founder Account Only | Logged in on production | 1. Observe production dashboard home | Dashboard displays real account metrics. NO test data injected. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. FOR FOUNDER USE ONLY | P1 | Production | Not Run |  |  |  |  | ch11/§5
S10-T007 | S10 — PRODUCTION READ-ONLY SMOKE | Production Contact Load | /contact | Unauthenticated | Browser open | 1. Navigate to https://aivilabs.com/contact | Contact page loads cleanly. DO NOT submit test form submissions on production. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Read-only verification | P2 | Production | Not Run |  |  |  |  | ch11/§5
S10-T008 | S10 — PRODUCTION READ-ONLY SMOKE | Production Payment Verification | /dashboard | Founder Account Only | ⚠️[FOUNDER-VERIFY] | 1. Founder verifies Razorpay Live Mode keys in Firebase project aivi-career console | ⚠️[FOUNDER-VERIFY] Founder verifies Razorpay Live Mode keys (rzp_live_...) in production server secrets. NO test transactions executed on live gateway. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. ⚠️[FOUNDER-VERIFY] Server secrets check | P0 | Production | Not Run |  |  |  |  | ch11/§5
S11-T001 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Staging Banner Check (Deprecating / Skipped) | N/A — No Staging Environment | Tester | N/A — Staging environment decommissioned | 1. Staging environment removed. All testing targets Production (aivilabs.com). 2. Skip banner check. | N/A — no staging environment; skip | N/A — Staging environment decommissioned. | P3 | Production | Skipped |  |  |  |  | ch09/§3
S11-T002 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Feature Flags Checklist Sanity | System Flags | Tester | Codebase inspection | 1. Inspect campusConfig.ts MODULE_FLAGS (core_ai, drives, sprints, voice_hi, vault, accreditation, sso, api, parent_reports) | All 9 module flags are set to default 'true'. None accidentally flipped off in production build. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check MODULE_FLAGS in campusConfig.ts (ch.09/§1) | P1 | Production | Not Run |  |  |  |  | ch09/§1
S11-T003 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Mobile Responsive Spot-Check | /dashboard & /campus | Tester | DevTools 375px | 1. Switch DevTools to 375px Mobile View 2. Test navigation on /dashboard and /campus portal | Dashboard sidebar collapses into accessible mobile drawer. Tables scroll horizontally without breaking screen bounds. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check use-mobile hook & Shadcn drawer | P2 | Production | Not Run |  |  |  |  | ch01/§5
S11-T004 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Campus Contrast & Readability | /campus/* | Tester | On campus portal | 1. Navigate across /campus dashboard, student directory, and drives pages 2. Inspect text contrast against dark theme background | All primary text, labels, and badges meet WCAG AA contrast standards. No dark text on dark background defects. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check contrastGuard.ts utility | P2 | Production | Not Run |  |  |  |  | ch01/§5
S11-T005 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | CSV Export Excel Compatibility | /campus/audit-logs | Tester | Export executed | 1. Export Audit Logs CSV or Student Roster CSV 2. Open downloaded .csv file in Microsoft Excel | CSV opens in Excel cleanly with correct column headers, UTF-8 character encoding, and proper cell line breaks. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check CSV formatting in services | P2 | Production | Not Run |  |  |  |  | ch06/Domain H
S11-T006 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Large Directory Scroll Performance | /campus/students | Tester | 240 students loaded | 1. Open /campus/students with 240 student records loaded 2. Scroll down rapidly to bottom of page | Page scrolls smoothly without lag, UI freezing, or excessive DOM re-renders. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check virtualized list or pagination rendering | P2 | Production | Not Run |  |  |  |  | ch02/Route-34
S11-T007 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Console Log Hygiene | Browser Console | Tester | DevTools Console open | 1. Perform auth, resume scoring, and campus navigation 2. Inspect DevTools Console logs | No uncaught runtime JavaScript exceptions or sensitive secrets/tokens printed in console. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check logSafeError in backend & client catch blocks | P2 | Production | Not Run |  |  |  |  | ch01/§1
S11-T008 | S11 — CROSS-CUTTING & REGRESSION SPOT CHECKS | Browser Refresh State Integrity | /dashboard/resume | Student 1 | Analysis displayed | 1. Complete resume scoring analysis 2. Press F5 (Browser Refresh) | App refreshes cleanly, maintains user session, and re-renders recent analysis from Firestore. | 1. confirm the URL bar shows https://aivilabs.com (production) 2. Check React Query caching & AuthContext init | P2 | Production | Not Run |  |  |  |  | ch01/§1

## Error Diagnosis Guide
AIVI CAREER & CAMPUS OS — MASTER ERROR CATALOGUE & QA DIAGNOSIS GUIDE
1. Master Error & Message Catalogue (From Chapter 08)
Error ID | Exact Message Text (Verbatim) | Screen / Component File | Precise Trigger Condition | Recommended User Action | Retryable
ERR-001 | An account with this email already exists. | Auth.tsx | Signup with email already registered in Firebase Auth | Click 'Sign In' instead or reset password | No
ERR-002 | Password should be at least 6 characters. | Auth.tsx | Signup password string length < 6 | Enter a stronger password (>=6 characters) | Yes
ERR-003 | Invalid email or password. | Auth.tsx | Auth sign-in failure (auth/invalid-credential) | Verify email and password credentials | Yes
ERR-004 | Email verification required. | ProtectedRoute.tsx | Authenticated user has emailVerified == false | Check inbox for verification link or click Resend | Yes
ERR-005 | Google sign-in popup was closed. | Auth.tsx | User closes Google OAuth popup window before completion | Re-click 'Continue with Google' | Yes
ERR-006 | Popup blocked by browser. Enable popups to sign in with Google. | Auth.tsx | Browser popup blocker prevents OAuth window | Allow popups for domain in browser settings | Yes
ERR-007 | If an account exists for this email, a reset link has been sent. | Auth.tsx | User submits password reset form | Check email inbox for password reset link | Yes
ERR-008 | Free tier limit reached. Upgrade to Starter or Pro for unlimited resume scoring. | ResumeIntelligence.tsx | Free user exceeds 2 lifetime resume analyses | Upgrade plan via Upgrade Modal | No
ERR-009 | Resume text is too short to analyze. | ResumeUploadForm.tsx | Uploaded/pasted resume text length < 50 characters | Provide a complete resume document | Yes
ERR-010 | AI service is temporarily unavailable. Please try again. | analysisService.ts | Gemini API timeout or backend error | Wait 10 seconds and re-click Analyze | Yes
ERR-011 | Please provide both a resume and a job description. | JobFitAnalysis.tsx | Job fit form submitted with missing resume or JD | Fill in both text fields before analyzing | Yes
ERR-012 | The linkedin optimize feature is only available on Starter or Pro plans. | functions/src/index.ts | Free user attempts LinkedIn profile rewrite | Upgrade to Starter or Pro subscription | No
ERR-013 | Rate limit exceeded. Try again in a minute. | functions/src/index.ts | User executes >3 AI analysis calls in 60 seconds | Wait 60 seconds before submitting next request | Yes
ERR-014 | Unable to load Razorpay checkout script. Please check your network or adblocker/CSP settings. | paymentService.ts | Razorpay JS fails to load within 10 seconds | Disable adblocker / check internet connection | Yes
ERR-015 | Failed to open Razorpay modal. Please check browser pop-up settings or retry. | paymentService.ts | Exception thrown when initializing Razorpay window | Allow popups or refresh page | Yes
ERR-016 | DPDP consent required before running AI analysis. | functions/src/security/auth.ts | Student user without DPDP consent triggers AI tool | Accept DPDP consent prompt in modal | Yes
ERR-017 | Access denied for role. | functions/src/security/auth.ts | Caller lacks required role claims for endpoint | Switch to authorized user account | No
ERR-018 | Access denied for branch. | functions/src/security/auth.ts | Coordinator accesses student outside branchScope | Request updated branch scope assignment | No
ERR-019 | Tenant seat limit reached. Upgrade campus plan to add more students. | functions/src/index.ts | CSV student import exceeds tenant seats quota | Upgrade institutional seat license | No
ERR-020 | Microphone access denied. Please enable mic permissions in browser settings to use voice mode. | CampusInterviews.tsx | User rejects browser microphone prompt | Grant microphone permission in browser bar | Yes
2. QA Diagnostic Scenarios (Symptom -> Cause -> Checks)
# | Observed User Symptom | Probable Root Cause | First Diagnostic Checks for QA Tester
1 | Login succeeds, but immediately redirects back to /verify-email | User's email is not verified in Firebase Auth | Check user.emailVerified in Firebase Console. Click 'Resend Email' and click link.
2 | Upgrade to Starter modal opens when clicking LinkedIn Optimizer | User is on Free plan (linkedin_optimize requires paid tier) | Check user_plans/{uid} document. Verify planType is 'starter' or 'pro'.
3 | AI Analysis fails with 'Rate limit exceeded' toast | User clicked Analyze >3 times in under 1 minute | Inspect Firestore collection ai_rate_limits/{uid}_careerAnalysis. Wait 60s for reset.
4 | Razorpay payment modal fails to launch after clicking Upgrade | Script blocked by browser adblocker or strict CSP policy | Open browser Developer Console. Check for blocked request to checkout.razorpay.com.
5 | Campus student cannot launch Vernacular Mock Interview | Student has not accepted DPDP Privacy Consent prompt | Check profiles/{uid} doc for dpdpConsent: true. Accept consent modal on screen.
6 | Coordinator cannot view CSE student profiles | Coordinator lacks 'CSE' in custom claim branchScope | Inspect JWT ID token claims or tenant_members doc. Verify branchScope array.
7 | CSV Student Import fails with 'Tenant seat limit reached' | CSV row count + seatsUsed exceeds tenant seats quota | Inspect tenants/{tenantId} document. Compare seatsUsed vs seats.
8 | Platform Admin Console displays 'Access Denied' | Account email is not listed in PLATFORM_ADMIN_ALLOWLIST | Verify email in functions/src/demoSeeder.ts. Run bootstrapPlatformAdmin endpoint.
9 | Vernacular Voice Interview fails to transcribe speech | Microphone blocked or Bhashini voice provider timeout | Check browser mic permissions. Verify network request to bhashini.gov.in.
10 | 1-Click Demo Campus seeder fails with 'Confirmation Required' | Tenant demo-sunrise already exists in Firestore | Inspect tenants/{tenantId}. Seeder execution is FOUNDER-ONLY on Production.
3. Protocol: If Nothing Here Matches Your Problem
1. Perform a hard browser refresh (Ctrl + Shift + R or Cmd + Shift + R) to clear cached JavaScript bundles.
2. confirm the URL bar shows https://aivilabs.com (production).
3. Test the exact same flow in an Incognito / Private window to rule out browser extension interference.
4. Try logging in with a different test account of the same role from the Test Accounts sheet.
5. Open Developer Console (F12) -> Console & Network tabs -> Capture screenshot of any red error stack trace.
6. File a bug on 'Bug Log' sheet using the mandatory 5-line format, attach screenshot link, and write 'checks done: hard refresh, incognito, console inspect'.

## Bug Log
AIVI CAREER & CAMPUS OS — FORMAL QA BUG LOG
Bug ID | Date | Found via Test ID | Module / Screen | Severity | Found By | ① What I did | ② What I expected | ③ What happened (exact message) | ④ URL + Env + Account | ⑤ Screenshot/recording link | Checks done before filing | Status | Dev Notes (founder/builder) | Retested By + Date
BUG-001 | 2026-07-23 | S01-T005 | Auth / Login | P2 | Intern Lead | 1. Navigated to https://aivilabs.com/login 2. Entered email 'test.unverified@demo.aivilabs.com' and password 'DemoUser@2026' 3. Clicked 'Sign In' | User should log in and land on /dashboard | Screen redirected to /verify-email showing banner 'Email verification required.' | https://aivilabs.com/login ¦ Production ¦ test.unverified@demo.aivilabs.com | https://drive.google.com/file/d/sample-bug-001/view | checks done: checked user in console, emailVerified is false, password is correct, email reset link arrives. Working as designed per ch.05. | Not a Bug | Expected behavior per Auth security rules (ch.05). Unverified accounts are strictly gated to /verify-email. | Founder / 2026-07-23
BUG-002
BUG-003
BUG-004
BUG-005
BUG-006
BUG-007
BUG-008
BUG-009
BUG-010
BUG-011
BUG-012
BUG-013
BUG-014
BUG-015
BUG-016
BUG-017
BUG-018
BUG-019
BUG-020
BUG-021
BUG-022
BUG-023
BUG-024
BUG-025
BUG-026
BUG-027
BUG-028
BUG-029
BUG-030
BUG-031
BUG-032
BUG-033
BUG-034
BUG-035
BUG-036
BUG-037
BUG-038
BUG-039
BUG-040
BUG-041
BUG-042
BUG-043
BUG-044
BUG-045
BUG-046
BUG-047
BUG-048
BUG-049
BUG-050
BUG-051
BUG-052
BUG-053
BUG-054
BUG-055
BUG-056
BUG-057
BUG-058
BUG-059
BUG-060
BUG-061

## Daily Report & Progress
AIVI CAREER & CAMPUS OS — TESTING PROGRESS DASHBOARD & DAILY LOG
1. Intern Daily Testing Execution Log
Date | Intern Name | Suite(s) Worked | TCs Executed | Passed | Failed | Blocked | Bugs Filed (IDs) | Blockers / Daily Notes
2. Automated Test Execution Progress Dashboard (Computed via Live Formulas)
Suite Name | Suite Description | Total TCs | Passed | Failed | Blocked | Not Run | % Complete | Gate Readiness Status
S00 | Daily Production Environment Smoke Suite
S01 | Authentication, Signup, Verification, SSO & Reset
S02 | 8 B2C SaaS AI Career Analysis Tools & Limits
S03 | Razorpay Order Creation, Checkout & Plan Updates (Founder Live Only)
S04 | Platform Admin Console, Provisioning & Seeder
S05 | Campus TPO Dashboard, Drives, CSV Import & Vault
S06 | Coordinator Branch-Scoped Access Control
S07 | Campus Student Portal, DPDP & Vernacular Voice
S08 | Public Marketing Pages, SEO Landing & Contact
S09 | Route Guards, Storage Rules & Header Security
S10 | Production Environment Read-Only Smoke Suite
S11 | Responsiveness, Contrast & Regression Spot-Checks
OVERALL TOTALS | All 12 Test Suites Combined
GATE 1 READY = S00–S03 100% executed, 0 open P0/P1 · GATE 2 = S04–S09 100% executed, 0 open P0 · GATE 3 = S10 read-only verified by founder